## Instructions
TEAM NAME	Elite
PROJECT NAME	Elektoo
PROJECT MENTOR	Ankit Aggarwal
TEAM MEMBERS	Aman Rai
	Ayushi Goyal
	Prachi Agrawal
	Vinay Singh

## Team_Status
TEAM NAME	Elite
PROJECT NAME	Elektoo
PROJECT MENTOR	Ankit Aggarwal

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 5 (August 31- sept 6)
Role preferences	Coordination	Vinay	0.5	0.5	Ongoing		0	0
Team Meeting	Coordination	Aman	2	3	Done		-1	3300.00%
Status tracker	Documentation	Prachi	1	1	Planned		0	0
High level requirements list creation	Documentation	Ayushi	7	2	Done	Need to trigger the documentation pace	5	2500.00%

Week 6 (Sept 7- sept 13)
Team Meeting	Coordination	Aman	1	1	Done		0	0.00%
SRS document preparation	Documentation	Vinay	12	14	Ongoing		-2	14.20%
Learning the technologies required	Development	Prachi	15	15	Ongoing		0	0.00%
Learning the technologies required	Development	Ayushi	7	5	Ongoing		2	40.00%

Week 8 (sept 14 - sept 20)
SRS document preparation and submission	Documentation	Vinay	12	10	Done	Documentation successfully submitted on time	2	50
setting up end to end skeleton flow	Interfaces	Ayushi	5	5	Ongoing		0	0
Learning the technologies required	Development	Prachi	18	20	Ongoing		-2	10
Working on front end UI	Interfaces	Aman	10	8	Ongoing		2	25

Week 9(sept 21 – sept 27)
setting up end to end skeleton flow	Interfaces	Ayushi	4	4	Done		0	0
Working on the auto-complete feature	Development	Prachi	5	3	Ongoing		2	66.66
Working on the basic search implementation	Interfaces	Aman	6	0	Planned		6	INF
Planning the basic layout of the web page	Design	Vinay	4	0	Planned		4	INF

Week 10(sept 28 – Oct - 4)
Working on the basic search implementation	Development	Aman	6	7	Ongoing		-1	14.2857142857
Working on the auto-complete feature	Development	Prachi	2	3	Done	Auto-complete feature implemented( only the beta version)	-1	33.3333333333
Planning the basic layout of the web page	Design	Vinay	4	3	Ongoing		1	33.33
Creating the presentation for first release	Preparation	Ayushi	2	1	Ongoing
Week 11(Oct 5 – Oct 11)
Creating the presentation for first release	Preparation	Ayushi	3	3	Done	Formal presentation for the first release of the application in progress	0	0
Working on the basic search implementation	Development	Aman	1	1	Done		0	0
Implementation for features for first release	Delivery	Prachi	5	4	Done	Features for first release implemented successfully	1	25
Planning the basic layout of the web page	Design	Vinay	1	1	Done		0	0

Week 12(Oct 12- Oct18)
Search for the algorithms for “search engine” implementation	Development	Aman	4	0	Planned		4	INF

Week 13(Oct 19 – Oct25)
Plan for further features implementation	Preparation	Ayushi	3	0	Planned	Plan for the features for final release required	3	INF
Search for the algorithms for “search engine” implementation	Development	Aman	4	0	Delayed	Need to work on the search features	4	INF

Week 14(Oct 26 – nov1)
Search for the algorithms for “search engine” implementation	Development	Aman	4	2	Ongoing		2	100
Plan for further features implementation	Preparation	Ayushi	3	1	Ongoing	More features need to be added to the application	2	200
Plan the design for further added features	Design	Vinay	3	1	Ongoing		2	200
Updating the status tracker	Documentation	Prachi	3	3	Done		0	0

Week 15(nov2 -nov8)						-1	14.2857142857
Search for the algorithms for “search engine” implementation	Development	Prachi	6	7	Done	need to code now the thought algorithm.	-3	37.5
making of the search query box	Development	Aman	5	8	Ongoing		-0.5	20
Algorithm for Choice Matrix	Development	Ayushi	3	4	Ongoing
UI of Choice Matrix	Design	Vinay	2	2.5	Done
Week 16(nov9 – nov15)						-4	23.5294117647
Implementation of the Search Query box	Development	Aman	13	17	Ongoing		-3	42.8571428571
UI of Elektoo	Development	Prachi	4	7	Ongoing	Continuing the implementation work	-3	37.5
Implementing Choice Matrix	Development	Vinay	5	8	Ongoing		-2	40
Integrating the wole application	Interfaces	Ayushi	3	5	Done
Week 17(nov16 – nov22)						-2	28.5714285714
Implementation for features for Second release	Delivery	Aman	5	7	Done		1	50
Finall look of the application(“Query Box”)	Development	Prachi	3	2	Done		1	16.6666666667
Implementation for 2nd release(“Choice Matrix”)	Delivery	Vinay	7	6	Done	Ready for the final presentation	0.5	33.3333333333
Final Presentaion for Release-2	Delivery	Ayushi	2	1.5	Done

## Individual_Status
TEAM NAME	Elite
PROJECT NAME	Elektoo
PROJECT MENTOR	Ankit Aggarwal

Activities	Aman Rai		Ayushi Goyal		Prachi Agrawal		Vinay Singh		Estimated Total Hours	Actual Total Hours
	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent
Week 5 (August 31- sept 6)
Team Meeting	0.5	1	0.5	1	0.5	1	0.5		2	3
High level requirements list creation	1.5	0.5	2	0.5	2	0.5	1.5	0.5	7	2

Week 6 (Sept 7- sept 13)
meetings	0.5	1	0.5	1	0.5	1	0.5	1	2	4
SRS document preparation	4	3	3	2.5	3	3	7	6	17	12.5
learning technologies	6	5	4	4	5	6	7	5	22	20

Week 8 (sept 14 - sept 20)
SRS document preparation and submission	2	3	3	2	1	1	4	3	10	9
learning technologies	6	8	4	3	3	2	6	8	19	21
setting up end to end skeleton flow	2	2	5	5	2	1	3	2	12	10

Week 9(sept 21 – sept 27)
setting up end to end skeleton flow	1	1	1	1	1	1	1	1	4	4
Working on the auto-complete feature	2.5	1.5	0	0	2.5	1.5	0	0	5	3
Working on the basic search implementation	1.5	0	1.5	0	1.5	0	1.5	0	6	0
Planning the basic layout of the web page	0	0	2	0	0	0	2	0	4	0

Week 10(sept 28 – Oct4)
Working on the basic search implementation	3	3.5	0	0	3	3.5	0	0	6	7
Working on the auto-complete feature	1	1.5	0	0	1	1.5	0	0	2	3
Planning the basic layout of the web page	0	0	2	1.5	0	0	2	1.5	4	3
Creating the presentation for first release	0	0	0.5	0.5	0	0	0.5	0.5	2	1

Week 11(Oct5 – Oct11)
Creating the presentation for first release	0	0	1.5	1.5	0	0	1.5	1.5	3	3
Working on the basic search implementation	0.5	0.7	0	0	0.5	0.3	0	0	1	1
Implementation for features for first release	2	1.5	0.5	0.5	2	1.5	0.5	0.5	5	4
Planning the basic layout of the web page	0	0	0.5	0.5	0	0	0.5	0.5	1	1

Week 12(Oct12 – Oct18)
Search for the algorithms for “search engine” implementation	1	0	1	0	1	0	1	0	4	0

Week 13(Oct19 -Oct25)
Plan for further features implementation	1	0	0.5	0	0.5	0	1	0	3	0
Search for the algorithms for “search engine” implementation	1	0	1	0	1	0	1	0	4	0

Week 14(Oct26 – nov1)
Search for the algorithms for “search engine” implementation	1	0.5	1	0.5	1	0.5	1	0.5	4	2
Plan for further features implementation	1	0	0.5	0.5	0.5	0.5	1	0	3	1
Plan the design for further added features	0.5	0	1	0.5	0.5	0	1	0.5	3	1
Updating the status tracker	0	0	0	0	2	2	1	1	3	3

Week 15(nov2 -nov8)
Search for the algorithms for “search engine” implementation	3	5	2	2	3	2	3	1
making of the search query box	4	3	4	5	0	0	0	0
UI of Choice Matrix	0	0	0	0	4	3	2	3		6
Week 16(nov9 – nov15)						3	0
Implementation of the Search Query box	5	8	6	7	1	1.5	3	2	15	21.5
UI of Elektoo	3	2.5	4	4	2	3	3	2.5	14	27
Implementing Choice Matrix	1	0.5	2	0.5	3	6	4	6	12.5	27
Integrating the wole application	3	2	1	2	3	2	2	1.5	15	20
Week 17(nov16 – nov22)						1.5	15
Implementation for features for Second release	5	7	3	6	4	4	7	6	19	24.5
Finall look of the application(“Query Box”)	2	3	4	2	2	1	2	0.5	16	25.5
Implementation for 2nd release(“Choice Matrix”)	1	1	1	0.5	5	4	3	3.5	10.5	25
Final Presentaion for Release-2	1	2	2	2	3	2	2	2	11.5	18.5

						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0